## Sheet1
[7 empty] | Development |  | Testing Defect Closure |  | Integrated Testing |  |  | Progress Status( % of Completion)
Resource Name | CR NO. | RFP Response Page Number | RFP Response Point Number | Task level Requirement | Module | Version (Original Plan) | Start Date | End Date | Start Date | End Date | Start Date | End Date | Effort(Man Days) | As on 4th Jan'08 | As on 7th Jan'08 | As on 8th Jan'08 | As on 9th Jan'08 | As on 10th Jan'08 | As on 11th Jan'08 | As on 14th Jan'08 | As on 15th Jan'08 | As on 16th Jan'08 | Remarks
shailesh | 35435 | 38 | 5 | System should enable definition of commissions computation formulae | Accounts | v2 | 2007-03-12 | 2007-05-12 | 26/12/2007 | 31/12/2007 | 26/12/2007 | 31/12/2007 | 4 | Done
Sanjib saha | 35435 | 56 | 6 | Able to remind users on outstanding premium for the policy | Accounts | v2 | [6 empty] | 6 | [9 empty] | Shifted to Phase III
Sanjib saha | 35435 | 92 | 14 | The system should prompt financial system for an accounts receivable entry in order to deal with short Premium Collection. | Accounts | v2 | [6 empty] | 3 | [9 empty] | Shifted to Phase III
Sailesh & Jay | 35191 | 94 | 3 | Facility to store withholding tax % | Accounts | v2 | 17/12/2007 | 26/12/2007 | 26/12/2007 | 31/12/2007 | 26/12/2007 | 31/12/2007 | 10 | Done
Shailesh | 35441 | 54 | 2 | Able to show in the Debit/Credit Note the Gross and Net premium, discount, commission and the service tax, tax and levy, coinsurance service charge, etc | Accounts | v3 | 21/1/2008 | 28/1/2008 | 28/01/2008 | 31/01/2008 | 28/01/2008 | 31/01/2008 | 6 | Yet to Start |  | Yet to Start
Sanjib saha | 35441 | 17 | 28 | Able to provide self explain account/agency code by branch/agent/broker/group/direct | Accounts | v3 | 21/1/2008 | 25/01/2008 | 28/01/2008 | 31/01/2008 | 28/01/2008 | 31/01/2008 | 16.5 | Yet to Start |  | Yet to Start |  |  |  | Yet to Start
Swarup | 35435 | 17 | 29 | Able to display last account code allocated to any branches/intermediary | Accounts | v2 | 2007-06-12 | 13/12/2007 | 26/12/2007 | 31/12/2007 | 26/12/2007 | 31/12/2007 | 7.5 | Done
Anindam | 35366 | 95 | 7 | Query facility available on cheque amount / bill number | Accounts | v2 | 2008-07-01 | 16/01/2008 | 16/01/2008 | 19/01/2008 | 19/01/2008 | 21/01/2008 | 4.5 | Yet to Start |  | 10% | 60% | 70% | 75% | 80% | 85% |  | Anindam prepare the RDF. Query will prepared by Sanjib(cheque), Sailesh(bill)
Swarup | 35435 | 56 |  | Data are integrated on-line for payment of refund premium and system electronically print refund cheque (with restricted users). Amount refund must not be greater than the original premium. | Accounts | v2 | [6 empty] | 13 | [9 empty] | Shifted to Phase IV
Swarup |  | 17 | 27 | Auto allocate and control account/agency code | Accounts | v3 | [6 empty] | 8.5 | [9 empty] | Need to defer (Phase IV)
Saikat | 35441 | 93 | 17 | Proposal is converted into Policy only when the sufficient balance is found in BG/CD. | Accounts | v3 | 21/1/2008 | 24/01/2008 | 28/01/2008 | 31/01/2008 | 28/01/2008 | 31/01/2008 | 4 | Yet to Start |  | Yet to Start | 100%
Saikat | 35441 | 94 | 33 | Time of issuance of receipt should be captured from the system | Accounts | v3 | 21/1/2008 | 25/01/2008 | 28/01/2008 | 31/01/2008 | 28/01/2008 | 31/01/2008 | 0.5 | Yet to Start |  | Yet to Start
Shailesh | 35441 | 95 | 1 | Ability to create masters for vendors | Accounts | v3 | 21/1/2008 | 28/01/2008 | 28/01/2008 | 31/01/2008 | 28/01/2008 | 31/01/2008 | 4 | Yet to Start |  | Yet to Start
Shailesh | 35441 | 95 | 4 | Payment is posted to GL automatically | Accounts | v3 | 21/01/2008 | 21/01/2008 | 28/01/2008 | 31/01/2008 | 28/01/2008 | 31/01/2008 | 0.5 | Yet to Start |  | Yet to Start
Swarup |  | 95 | 8 | Maintenance of user ID for security and statistical purposes | Accounts | v3 | [6 empty] | 0.5 | [9 empty] | Generic requirement
Swarup |  | 97 | 9 | Statement of account reflecting matched transactions and outstanding transaction | Accounts | v3 | [6 empty] | 3.5 | [9 empty] | Need to defer (Phase IV)
Anindam | 35202 | 97 | 3 | Statement indicate either agent, broker, outwards or inwards reinsurance, coinsurance, claim recovery etc. | Accounts | v2 | 2008-07-01 | 16/01/2008 | 16/01/2008 | 19/01/2008 | 19/01/2008 | 21/01/2008 | 12.5 | Started | 10% | 20% | 25% | 40% | 60% | 70% | 70% |  | Anindam will prepare necessary RDF. Qry Sanjib & Sailesh
Shailesh | 35207 | 98 | 13 | System to provide month-end earned and unearned premium | Accounts | v2 | 19/12/2007 | 26/12/2007 | 26/12/2007 | 31/12/2007 | 26/12/2007 | 31/12/2007 | 5.5 | Done
Shailesh | 35441 | 97 | 1 | Able to provide Claims and non-claims Statement | Accounts | v3 | 21/1/2008 | 25/01/2008 | 28/01/2008 | 31/01/2008 | 28/01/2008 | 31/01/2008 | 10 | Yet to Start |  | Yet to Start
Shailesh | 35200 | 97 | 2 | Option to statement ‘Open item’ or ‘B/F Balance’ basis. | Accounts | v3 | [6 empty] | 9 | [9 empty] | Need to defer (Phase IV)
Sanjib saha | 35435 | 93 | 20 | In case of Co-insurance transaction, the co-insurance accounts are accordingly updated. | Accounts | v2 | 2007-06-12 | 2007-12-12 | 26/12/2007 | 31/12/2007 | 26/12/2007 | 31/12/2007 | 5.5 | Done |  |  |  | 50% | 50% | 100% | 100%
Sanjib saha | 35435 | 93 | 21 | Multiple collection for multiple Policies in a single receipt is possible provided the Insured is same | Accounts | v2 | 2007-12-12 | 17/12/2007 | 26/12/2007 | 31/12/2007 | 26/12/2007 | 31/12/2007 | 8 | Done
Anindam | 35203 | 97 | 4 | Statement ageing – option for inception or booking date | Accounts | v2 | 2008-07-01 | 16/01/2008 | 16/01/2008 | 19/01/2008 | 19/01/2008 | 21/01/2008 | 8 | Started | 10% | 15% | 15% | 15% | 20% | 40% | 60% |  | RDF required to develop
Saikat | 35441 | 92 | 11 | Cancellation of receipt is done in receipt screen and the entry in cashbook is reversed automatically. | Accounts | v3 | 17/01/2008 | 24/1/2008 | 28/01/2008 | 31/01/2008 | 28/01/2008 | 31/01/2008 | 7.5 | Yet to Start
|  | 92 | 13 | The system should provide for premium collected in advance where the policy is issued in the current year for the risk commencing in the next financial year. In such case the premium collected in the current year is accounted as advance premium and the same is reversed on the first day of the new financial year automatically | Accounts | v3 | [6 empty] | 9.5 | [9 empty] | Need to defer (Phase IV)
Shailesh | 35441 | 96 | 17 | Tax deducted at source at the specified rate to be computed and accounted for in respect of payments to specified professionals | Accounts | v3 | 21/01/2008 | 22/01/2008 | 28/01/2008 | 31/01/2008 | 28/01/2008 | 31/01/2008 | 1.5 | Yet to Start
Saikat | 35441 | 96 | 18 | The disbursement to the insured should take care of Salvage recovery | Accounts | v3 | 22/01/2008 | 25/01/2008 | 28/01/2008 | 31/01/2008 | 28/01/2008 | 31/01/2008 | 3 | Yet to Start |  |  | 70%
Sanjib saha | 35447 | ‘2.1.2.3.’ | URS 1.2 | For direct policy by dealer, tagging has to happen while issuing policy but acceptance will happen later. So normal is acceptance followed by tagging but the reverse will also be required | Accounts | v3.1 | 2008-02-01 | 2008-10-01 | 2008-11-01 | 14/01/2008 | 15/01/2008 | 18/01/2008 |  | 15% |  |  |  |  | pending |  |  |  | Confirmation pending from Anjali Ghurey & P. K. Paramanik. Confirmed at 4.30 PM
Saikat | 35447 | ‘2.1.2.7’ | URS 1.2 | Cash deposit, instrument deposit (Cheque/ Draft), BG, Credit Card, Direct debit facilities required. Direct debit from Account can be provided later. This is same as standing instruction and is somewhat similar to CD Account. | Accounts | v3.1 | 28/12/2007 | 31/12/2007 | 2008-02-01 | 2008-02-01 | 15/01/2008 | 18/01/2008 |  | Done
Saikat | 35447 | ‘2.1.2.6.’ | URS 1.2 | USGI will like BRS to be uploaded from the banks. This will be as per format supplied by CMC | Accounts | v3.1 | 28/12/2007 | 31/12/2007 | 2008-02-01 | 2008-02-01 | 15/01/2008 | 18/01/2008 |  | Done
Sanjib Saha | 35447 | ‘2.1.2.7’ | URS 1.2 | Collection needs to be bifurcated between premium, salvage, miscellaneous etc. It needs to be captured while capturing the collection details. The collection type may be directly related to bank account, e.g., premium to one bank account and salvage to another. | Accounts | v3.1 | 2008-02-01 | 2008-10-01 | 2008-11-01 | 14/01/2008 | 15/01/2008 | 18/01/2008 |  | 50% |  | 90% | 100%, Tested,OK |  |  | 100%
Shailesh | 35447 | ‘2.1.2.1.1’ | URS 1.2 | Refund should by default be made in the customer’s name irrespective of whether the business is direct or thru intermediary. However, the payee can be overwritten by USGI | Accounts | v3.1 | 2008-02-01 | 2008-07-01 | 2008-11-01 | 14/01/2008 | 15/01/2008 | 18/01/2008 |  | 70% |  | 80% |  | 85% | 85% | 85% | 85% | 100% | part testing going on
Shailesh | 35447 | ‘2.1.2.1.1’ | URS 1.2 | Business location should be populated based on the policy number | Accounts | v3.1 | 2008-07-01 | 2008-10-01 | 2008-11-01 | 14/01/2008 | 15/01/2008 | 18/01/2008 |  | Yet to Start |  |  |  | 70% | 70% | 70% | 70% | 100%
Shailesh | 35447 | ‘2.1.2.1.1’ | URS 1.2 | Payee address and insured address may be different | Accounts | v3.1 | 2008-07-01 | 2008-10-01 | 2008-11-01 | 14/01/2008 | 15/01/2008 | 18/01/2008 |  | Yet to Start |  |  |  | 70% | 70% | 70% | 70% | 100%
Saikat | 35447 | ‘2.1.2.1.3’ | URS 1.2 | Viewing facility required for all endorsement and refund details | Accounts | v3.1 | 2008-02-01 | 2008-04-01 | 2008-04-01 | 2008-04-01 | 15/01/2008 | 18/01/2008 |  | 70% |  | 100% | Done | [5 empty] | Integrated Testing Pending
Saikat | 35447 | ‘2.1.2.1.3’ | URS 1.2 | Report required on ‘Instance Type’ and not ‘CD Type’. More clarification required | Accounts | v3.1 | 27/12/2007 | 28/12/2007 | 28/12/2007 | 28/12/2007 | 15/01/2008 | 18/01/2008 |  | Done
Sanjib saha | 35447 | ‘2.1.2.1.3’ | URS 1.2 | Process should be automated for non CD payment More clarification required | Accounts | v3.1 | 2008-04-01 | 2008-10-01 | 2008-11-01 | 14/01/2008 | 15/01/2008 | 18/01/2008 | [5 empty] | N/A |  |  |  |  | No different payment mode for CD. CD Payment requirement is handel by current avilable system facility.
Shailesh | 35447 | ‘2.1.2.1.3’ | URS 1.2 | Given that payment / refund terminates in GENISYS Configurator, refund can happen only for confirmed cases. | Accounts | v3.1 | 28/12/2007 | 31/12/2007 | 2008-02-01 | 2008-02-01 | 15/01/2008 | 18/01/2008 |  | Done
Shailesh | 35447 | ‘2.1.2.1.3’ | URS 1.2 | TDS to be deducted with each payment | Accounts | v3.1 | 2008-04-01 | 2008-07-01 | 2008-08-01 | 2008-11-01 | 15/01/2008 | 18/01/2008 |  | Started | 30% | 30% | 30% | 45% | 50% | 50% | 90% | 100%
Saikat | 35447 | ‘2.1.2.2.2’ | URS 1.2 | ‘BG Entry’ should be changed to ‘BG Tagging to Proposal’ | Accounts | v3.1 | 31/12/2007 | 2008-02-01 | 2008-02-01 | 2008-02-01 | 15/01/2008 | 18/01/2008 |  | Done
Sanjib saha | 35447 | ‘2.1.2.2.2’ | URS 1.2 | BG should not be used for any purpose after expiry date | Accounts | v3.1 | 2008-07-01 | 2008-11-01 | 2008-11-01 | 14/01/2008 | 15/01/2008 | 18/01/2008 |  | Yet to Start |  |  | 25% | 80% | 100% |  | 100%
Swarup | 35447 | ‘2.1.2.2.2’ | URS 1.2 | For house bank, transaction type should be only ‘Deposit to bank’ for branches. For central location there will be two entries. | Accounts | v3.1 | 28/12/2007 | 31/12/2007 | 31/12/2007 | 2008-02-01 | 15/01/2008 | 18/01/2008 |  | Done
Shailesh | 35447 | ‘2.1.1.6’ | URS 1.2 | ‘Bank Id creation’ should be modified to ‘Intermediary Credit Limit Specification’ | Accounts | v3.1 | 28/12/2007 | 31/12/2007 | 31/12/2007 | 2008-02-01 | 15/01/2008 | 18/01/2008 |  | Done
Shailesh | 35447 | ‘2.1.1.4’ | URS 1.2 | What about Merchant bank..to be discussed…. | Accounts | v3.1 | 2008-04-01 | 2008-08-01 | 2008-08-01 | 2008-08-01 | 15/01/2008 | 18/01/2008 |  | 80% |  | 80% |  | 90% | 90% | 90% | 90% | 100% | Clarification Pending
Saikat | 35447 |  | URS 1.2 | Transaction Id as such should not appear in master. However, USGI will decide on retaining this information upon getting explanation from CMC about the usage of this information | Accounts | v3.1 | 31/12/2007 | 2008-02-01 | 2008-02-01 | 2008-02-01 | 15/01/2008 | 18/01/2008 |  | Done
Shailesh |  |  |  | Testing for excel sheet upload in system | Accounts | unplanned one | 2008-08-01 | 2008-09-01 | 2008-09-01 | 2008-09-01 | 28/01/2008 | 31/01/2008 |  |  |  | 80% | 90% | 90% | 90% | 90% | 90%
Shailesh |  |  |  | Adding facility to save payment details in agent commisssion | Accounts | unplanned one | 2008-09-01 | 2008-09-01 | 2008-09-01 | 2008-09-01 | 28/01/2008 | 31/01/2008 |  |  |  |  | 80% | 80% | 80% | 90% | 90% | 100%
Shailesh |  |  |  | Display with hold tax and service tax in grid | Accounts | unplanned one | 14/01/2008 | 15/01/2008 | 15/01/2008 | 15/01/2008 | 28/01/2008 | 31/01/2008 | [7 empty] | 70% | 90% | 100%
Saikat |  |  | URS 1.2 | Testing for URS 1.2 delivery | Accounts | v3.1 | 14/01/2008 | 18/01/2008 | 18/01/2008 | 18/01/2008 | 19/01/2008 | 19/01/2008 | [8 empty] | 10%
Note on R29: wings: Wrongly updated. Yet to start
Note on S46: wings: On developer testing
Note on S48: wings: Claim payment checking pending
Note on T30: wings: Pending confirmation from Mumbai team
Note on U34: wings: Testing pending from Saikat
Note on U35: wings: Testing pending from Saikat
Note on U36: wings: Testing pending from Saikat
Note on U46: wings: Testing pending from Saikat
Note on U48: wings: Claim related development pending. No confirmation from Mumbai regarding BRS format
Note on U49: wings: Testing pending from Saikat
Note on U50: wings: Testing pending from Saikat
Note on V23: wings: Testing by Saikat
Note on V34: wings: Testing by Saikat
Note on V35: wings: Testing by Saikat
Note on V36: wings: Testing by Saikat
Note on V41: wings: Testing going on
Note on V43: wings: Testing by Saikat
Note on V46: wings: Testing going on
Note on V48: wings: Claim related development pending. No confirmation from Mumbai regarding BRS format
Note on V49: wings: Testing by Saikat
Note on V50: wings: Testing by Saikat